## Actor-Usecase
USESCASE POINT ESTIMATION
Project Code |  |  |  | Supervisor
Project Name |  |  |  | Customer
I. Summary
Unadjusted Actor Weight (UAW) |  |  | 9 | Total UCP | 721.2755
Unadjusted Use-Case Weight (UUCW) |  |  | 650 | Estinmation Effort (manhour) | 5770.204
Technical Complexity Factor (TCF) |  |  | 1.1 | Number of Member | 5
Environmental Complexity Factor (ECF) |  |  | 0.995 | Average Effort for each member | 1154.0408
I. Actor List
Unadjusted Actor Weight (UAW) |  |  | 9
No | Actor Name | Difficulty | Weight | Type | Description
1 | Admin | Average | 2 | Human
2 | Staff | Complex | 3 | Human
3 | Driver | Simple | 1 | Human
4 | Customer | Simple | 1 | Human
5 | Car Owner | Simple | 1 | System
6 | System Handler | Simple | 1 | Human
II. Usecase List
Unadjusted Use-Case Weight (UUCW) |  |  | 650
No | Actor | UC Name | Difficulty | Priority | Weight | Description
1 | Customer, Staff, Manager | Login | Complex | Must Have | 15
2 |  |  | Simple | Must Have | 5
3 |  |  | Simple | Should Have | 5
4 |  |  | Simple | Must Have | 5
5 |  |  | Simple | Must Have | 5
6 |  | Manage account (CRUD + Search) | Complex | Should Have | 15
7 |  |  | Simple | Should Have | 5
8 |  |  | Simple | Must Have | 5
9 |  |  | Simple | Must Have | 5
10 |  |  | Simple | Must Have | 5
11 |  |  | Simple | Must Have | 5
12 | Customer | Book service | Simple | Must Have | 5
13 |  |  | Simple | Must Have | 5
14 |  |  | Simple | Must Have | 5
15 |  |  | Simple | Must Have | 5
16 |  |  | Simple | Must Have | 5
17 |  |  | Simple | Must Have | 5
18 |  |  | Simple | Must Have | 5
19 |  |  | Simple | Must Have | 5
20 |  |  | Simple | Must Have | 5
21 |  |  | Simple | Must Have | 5
22 |  |  | Simple | Must Have | 5
23 |  |  | Simple | Must Have | 5
24 |  |  | Simple | Must Have | 5
25 |  |  | Simple | Must Have | 5
26 |  |  | Simple | Must Have | 5
27 |  |  | Simple | Must Have | 5
28 |  |  | Simple | Must Have | 5
29 |  |  | Simple | Must Have | 5
30 |  |  | Simple | Must Have | 5
31 |  |  | Simple | Must Have | 5
32 |  |  | Simple | Must Have | 5
33 |  |  | Simple | Must Have | 5
34 |  |  | Simple | Must Have | 5
35 |  |  | Simple | Must Have | 5
36 |  |  | Simple | Must Have | 5
37 |  |  | Simple | Must Have | 5
38 |  |  | Average | Must Have | 10
39 |  |  | Average | Must Have | 10
40 |  |  | Average | Must Have | 10
41 |  |  | Average | Must Have | 10
42 |  |  | Simple | Must Have | 5
43 |  |  | Simple | Must Have | 5
44 |  |  | Simple | Must Have | 5
45 |  |  | Simple | Must Have | 5
46 |  |  | Average | Must Have | 10
47 |  |  | Average | Must Have | 10
48 |  |  | Simple | Must Have | 5
49 |  |  | Average | Must Have | 10
50 |  |  | Average | Must Have | 10
51 |  |  | Simple | Must Have | 5
52 |  |  | Average | Must Have | 10
53 |  |  | Average | Must Have | 10
54 |  |  | Simple | Must Have | 5
55 |  |  | Complex | Must Have | 15
56 |  |  | Complex | Must Have | 15
57 |  |  | Simple | Must Have | 5
58 |  |  | Simple | Must Have | 5
59 |  |  | Simple | Must Have | 5
60 |  |  | Simple | Must Have | 5
61 |  |  | Simple | Must Have | 5
62 |  |  | Simple | Must Have | 5
63 |  |  | Simple | Must Have | 5
64 |  |  | Simple | Must Have | 5
65 |  |  | Simple | Must Have | 5
66 |  |  | Simple | Must Have | 5
67 |  |  | Simple | Must Have | 5
68 |  |  | Simple | Must Have | 5
69 |  |  | Simple | Must Have | 5
70 |  |  | Simple | Must Have | 5
71 |  |  | Simple | Must Have | 5
72 |  |  | Simple | Must Have | 5
73 |  |  | Simple | Must Have | 5
74 |  |  | Simple | Must Have | 5
75 |  |  | Simple | Must Have | 5
76 |  |  | Simple | Must Have | 5
77 |  |  | Simple | Must Have | 5
78 |  |  | Simple | Must Have | 5
79 |  |  | Simple | Must Have | 5
80 |  |  | Simple | Must Have | 5
81 |  |  | Simple | Must Have | 5
82 |  |  | Simple | Must Have | 5
83 |  |  | Simple | Must Have | 5
84 |  |  | Simple | Must Have | 5
85 |  |  | Simple | Must Have | 5
86 |  |  | Simple | Must Have | 5
87 |  |  | Simple | Must Have | 5
88 |  |  | Simple | Must Have | 5
89 |  |  | Simple | Must Have | 5
90 |  |  | Simple | Must Have | 5
91 |  |  | Simple | Must Have | 5
92 |  |  | Simple | Must Have | 5
93 |  |  | Simple | Must Have | 5
94 |  |  | Simple | Must Have | 5
95 |  |  | Simple | Must Have | 5
96 |  |  | Simple | Must Have | 5
97 |  |  | Simple | Must Have | 5
98 |  |  | Average | Should Have | 10
99 |  |  | Simple | Must Have | 5
100 |  |  | Simple | Must Have | 5
101 |  |  | Simple | Must Have | 5
102 |  |  | Simple | Must Have | 5
103 |  |  | Simple | Must Have | 5
104 |  |  | Simple | Must Have | 5
105 |  |  | Simple | Must Have | 5
106 |  |  | Simple | Must Have | 5
107 |  |  | Simple | Must Have | 5
108 |  |  | Simple | Must Have | 5
109 |  |  | Simple | Must Have | 5
110 |  |  | Simple | Must Have | 5
111 |  |  | Simple | Must Have | 5

## UCP Estimate
Technical Factor | Weight | Relevance 0-5 | Score
T1 Distributed System | 2 | 5 | 10
T2 Performance | 1 | 4 | 4
T3 End User Efficiency | 1 | 3 | 3
T4 Complex Internal Processing | 1 | 3 | 3
T5 Reusability | 1 | 4 | 4
T6 Easy to Install | 0.5 | 4 | 2
T7 Easy to Use | 0.5 | 4 | 2
T8 Portability | 2 | 3 | 6
T9 Easy to Change | 1 | 4 | 4
T10 Concurrency | 1 | 3 | 3
T11 Special Security Features | 1 | 3 | 3
T12 Provides Direct Access for Third Parties | 1 | 3 | 3
T13 Special User Training Facilities Are Required | 1 | 3 | 3
Sum |  |  | 50
Complexity Factor |  |  | 0.6
C2 |  |  | 0.01
TCF |  |  | 1.1
Environmental Factor | Weight | Impacte 0-5 | Score
E1 Familiarity With UML | 1.5 | 3 | 4.5
E2 Part-Time Workers | -1 | 3 | -3
E3 Analyst Capability | 0.5 | 3 | 1.5
E4 Application Experience | 0.5 | 3 | 1.5
E5 Object-Oriented Experience | 1 | 3 | 3
E6 Motivation | 1 | 3 | 3
E7 Difficult Programming Language | -1 | 3 | -3
E8 Stable Requirements | 2 | 3 | 6
Sum (ETF) |  |  | 13.5
ECF = 1.4 +(-0.03 * Environmental Total Factor) |  |  | 0.995
PF (Historical based average man hours per use case point) |  |  | 8 | manhour
Estimation Usecase Point (UCP = UUCP * TCF * ECF) |  | 721.2755
Estimation Effort (manhours) |  | 5770.204

## References
I. Actor
No | Difficulty | Multiplier | Description
1 | Simple | 1 | Simple actors are other systems that communicate with your software via a pre-defined API. An API could be exposed through a dll, or as a REST, SOAP, or any web-service API or remote procedure call (RPC). The key element is that you are exposing interaction with your software through a specific, well-defined mechanism.
2 | Average | 2 | Average actors can either be human beings interacting in a well defined protocol, or they could be systems that interact through a more complex or flexible API.
3 | Complex | 3 | The original definition of complex actors specifies that users who interact with the software through a graphical user interface are complex actors. While that is true, the same classifcation should apply to users who interact with the system in unpredictable ways. An AJAX interface that exposes more of the underlying application (and data stores) than would be available through a rigid protocol might introduce similar complexity.
II. Usecase
No | Difficulty | Multiplier | Description
1 | Simple | 5 | Simple Use Case - up to 3 transactions.
2 | Average | 10 | Average Use Case - 4 to 7 transactions.
3 | Complex | 15 | Complex Use Case - more than 7 transactions.
III. MoSCoW Prioritisation
No | Rules | Priority | Description
1 | Must Have | High | Requirements labelled as Must have are critical to the current delivery timebox in order for it to be a success. If even one Must have requirement is not included, the project delivery should be considered a failure
2 | Should Have | Medium | Requirements labelled as Should have are important but not necessary for delivery in the current delivery timebox.
3 | Could Have | Low | Requirements labelled as Could have are desirable but not necessary and could improve the user experience or customer satisfaction for a little development cost.
4 | Won’t Have this time | Very Low | Requirements labelled as Won't have, have been agreed by stakeholders as the least-critical, lowest-payback items, or not appropriate at that time.